## Slide 1: ARTICLE 5. Middle School Building Project
ARTICLE 5: Middle School Building Project
Motion: As printed in the handout

## Slide 2: Project Highlights: Educational Programming
Design enrollment 700 students for grades 6-8
Supports implementation of the Team-Teaching Model to meet the Ed Plan
1 grade level per floor; 3 teams per grade level; integrated SPED spaces
Inclusive design to serve students of all abilities
ARTICLE 5: Middle School Building Project

## Slide 3: Project Highlights: Educational Programming, continued
Classrooms with significant natural light
Connection with nature through integrated design concepts and expose to surrounding forest
Media Center equal to the existing middle school libraries combined; located in the heart of the school
Co-located Art & World Languages
ARTICLE 5: Middle School Building Project

## Slide 4: Project Highlights: Sustainability
Net Zero Ready Energy
  Predicted EUI of 25 kBtu/SF/yr
  Highly insulated exterior enclosure
  with triple pane windows
  All electric heating and cooling
Photovoltaic system readiness
Water reduction measures
Bioswales and native plantings
Sustainability measures equivalent
to LEEDv4 Certifiable
ARTICLE 5: Middle School Building Project

## Slide 5: Project Highlights: Public Spaces
“Public” wing for community use after hours
1 MIAA court with 2 large cross courts
420 seat auditorium
Natural grass athletic fields
ARTICLE 5: Middle School Building Project

## Slide 6: Project Schedule
ARTICLE 5: Middle School Building Project

## Slide 7: Concord Middle School – Current Scope *Consistent with scope approved at the Special Town Meeting in January 2022, less Value Management accepted in Design Development and 60% CD Phases
Current Cost
Current Cost including $6,184,098 VM Decisions to Date
$108.3M
Includes $86M construction cost, soft costs, contingencies @ 5% and a $2M bid contingency
ARTICLE 5: Middle School Building Project

## Slide 8: Budget vs. Current Cost Estimate @ 60% Design
STM Budget
January 2022
$102,815,697
60% CD Estimate
October 2022
$108,379,238
$5,563,541 Overrun
Scope Cut @ Increased Cost Why?
ARTICLE 5: Middle School Building Project

## Slide 9: Construction Costs are impacted by Market Inflation
Source: AGC Construction Inflation Alert
ARTICLE 5: Middle School Building Project
“What has contributed to
these extreme cost increases?
In brief: nearly everything.”
Contributors to runaway costs

## Slide 10: Greater Boston Commercial Construction Market
Source: ENR Quarterly Report
ARTICLE 5: Middle School Building Project
The average year over year inflation for commercial construction in Boston in 2021-22 was 8.7%.
Over the last decade, the average year over year inflation rate was 3.1%.
We have seen
unprecedented
inflation in 2022!

## Slide 11: Comparable Recent Construction Project Bids
ARTICLE 5: Middle School Building Project
Elementary School - Swampscott
Construction Budget: $76.5m
Construction Bid: $79.7m
Bid received October 2022(+4.1%)
DBB
High School: 90% CD - Stoneham
Construction Budget: $153.4m
Construction Estimate 90CD: $163.4m (+6.5%)
90 % Estimate Sept, Bid December 2022
Submitted 90% CD, added outside funding, significant VE, Stadium Building bidding as Alternate, re-allocated contingencies CMAR

## Slide 12: Comparable Recent Construction Project Bids
ARTICLE 5: Middle School Building Project
Mid-Size Regional High School – Nauset
Construction Budget: $105m
Construction Bid: FSB only $20m
Bid received June 2022 (+20%)
No HVAC bids received, Bid Protests, District moving Bid date out 3-4 months and seeing additional funds DBB
Large Suburban Elementary School – Andover
Construction Budget: $119.2m
Construction Bid: $136.2m
(+14%)
Significant VE at DD & 60%. STM scheduled Dec 1, 2022
CMAR

## Slide 13: Comparable Recent Construction Project Bids
ARTICLE 5: Middle School Building Project
Large Suburban Elementary School – Groton
Construction Budget: $61.0m
Construction Bid: $70.5m
(+15.6%)
Based on 60% CD in August 2022
Approved 9.5M at STM 9.12.22
CMAR
Suburban Elementary School – Westwood
Construction Budget: $70.0m
Construction Bid: $74.0m
Bid received July 2022 (+5.7%) Used ARPA and other Town Funds to bridge gap
DBB

## Slide 14: Comparable Recent Construction Project Bids
ARTICLE 5: Middle School Building Project
Middle School - Concord
Construction Budget: $80.7m
Construction Estimate (DD): $86m
(+6.5%)
Significant VE & Going back to Town for additional funds
DBB
Middle School - Somerset
Construction Budget: $69m
Construction Bid: $79m
Bid received July 2022 (+14.5%)
Failed vote at STM August 22
CMAR

## Slide 15: Looking Forward to 2023 - Observation: Inflation appears to be flattening
ARTICLE 5: Middle School Building Project

## Slide 16: Value Management January 2021 thru October 2022 $6,184,098 total estimated savings
ARTICLE 5: Middle School Building Project
SUMMARY OF ACCEPTED VALUE MANAGEMENT
2021 $ 2,180,100 Feasibility Study - completed April 2021
$1,740,145 Schematic Design – completed Nov 2021
2022 $1,879,261 Design Development – completed June 2022
$384,592 60% CD Estimate – completed October 2022
$6,184,098 Total (Construction Cost Savings)

## Slide 17: Concord Middle School Project – Year in Review
ARTICLE 5: Middle School Building Project

## Slide 18: RECAP: Warrant Article Timeline & Next Steps
ARTICLE 5: Middle School Building Project
October 27, 2022 - CMSBC recommendation to Select Board @ $115M
October 28, 2022 - Select Board vote for Warrant Article @ $110M (Current Warrant Amount)
January 13, 2023 - 90% CD Estimate to CMSBC
  If estimate < $110M, then proceed with $110M NTE budget
  If estimate > $110M, then TBD (CMSBC to discuss strategy 11.17 with likely deduct alts)
January 17, 2023 – Motions posted for Special Town Meeting
January 19, 2023 – Special Town Meeting
Date to be Announced – Special Town Vote

## Slide 19: If Article Doesn’t Pass
ARTICLE 5: Middle School Building Project
Financial Impact
Construction inflation ~ 0.7% month
  For a 6-9 month delay, this corresponds to a $3.6M - $5.4M increase in construction costs
CPS spends ~$50K per month on operating costs for existing MS
  For a 6-9 month delay, this corresponds to $300K - $450K in operating costs
Redesign will cost ~$600K
Total estimated cost impact is $4.5M - $6.5M depending on the duration of the delay

## Slide 20: If Article Doesn’t Pass
ARTICLE 5: Middle School Building Project
Schedule Impact
Estimated 6-9 Month Schedule Delay
Redesign to get back to $102.8M budget
Redo pre-qualification process
  Statement of Qualifications are only valid for 90 days after opening
  Projected School Opening Sept 2025 in lieu of Feb 2025

## Slide 21: If Article Doesn’t Pass
ARTICLE 5: Middle School Building Project
STM Vote Fails, Revert Back to $102.8M Budget
$108.7M Current Cost Estimate @ 60% CD
plus ~ $5.5M Cost for 6-9 Month Schedule Delay
equals $114.2M
Minus ~$11.4M scope reduction required to get “Back to Budget”
Equals $102.8M
Significant Scope Reduction

## Slide 22: RECAP: Feasibility Study Value Management $2,180,100 total estimated savings
ARTICLE 5: Middle School Building Project
SUMMARY OF DECISIONS
Remove ALT PE
2,400 GSF @ $559/SF
Remove Maker Space
1,500 GSF @ $559/SF
Remove Alt PE SF
Remove Maker Space SF

## Slide 23: RECAP: Schematic Design Value Management $1,740,145 total estimated savings
ARTICLE 5: Middle School Building Project
SUMMARY OF ACCEPTED VALUE MANAGEMENT
Stockpile existing soils on site
Reduce wood-look metal ceilings
Eliminate wood wall paneling in the Media Center
Eliminate CMU walls in back-of-house spaces and Gym
Eliminate roof screens
Remove 934 GSF from building footprint
Reduce height of glazing at connector

## Slide 24: RECAP: Design Dev. Value Management $1,879,261 total estimated savings
ARTICLE 5: Middle School Building Project
SUMMARY OF ACCEPTED VALUE MANAGEMENT
Reduce outdoor classrooms from 4 to 3 and remove bollard lighting
Reduce advanced lighting controls from 100% addressable to 60%
Remove interior light shelf
Replace certain curtain wall sections with punched windows

## Slide 25
ARTICLE 5: Middle School Building Project
SUMMARY OF ACCEPTED VALUE MANAGEMENT Continued
Change concrete foundation finish, eliminate green screen/trellis
Misc. plumbing and electrical material changes, combined AHU’s
Targeted reduction in insulation materials
Replace built-in shelving in Media Center with FF&E shelving
Ceramic tile changes in the kitchen and bathrooms
Reduction in the height of the Gym by 5 feet
Eliminate vape system detection and proprietary master clock system
Reduce Auditorium and Specialty Space AV by 15%
Other misc. changes in scope.

## Slide 26
ARTICLE 5: Middle School Building Project
RECAP: 60% CD Value Management
$384,592 total estimated savings
SUMMARY OF ACCEPTED VALUE MANAGEMENT
Replaced all wood-look metal
ceilings with 2x2 acoustical tile
Replaced 57 granite bollards with
concrete/steel bollards with stainless steel sleeves
Eliminated bleachers in Gymnasium
Eliminated environmental graphics

## Slide 27: ARTICLE 5. Middle School Building Project
ARTICLE 5: Middle School Building Project
Motion: As printed in the handout